## Sheet1
Project Start Date |  |  | 2020-05-04 |  |  |  | To be filled
Today |  |  | 2020-05-17 |  |  |  | Calculated
|  | Project Details | [5 empty] | Chart |  |  |  | Chart Values
Task Name |  | Start | End | Responsible | Deliverable | Completion |  |  | Is Event | Is Done | Ref. Date | White | Event Pending | Event Done | Task Length | Completed | Progress | Remaining | Today | Today
PreWar | [18 empty] | 10 | 3.4672
| Delage D8 120 | 2020-05-04 | 2020-05-22 | A | Frame | 0% |  |  | 0 | 0 | 2020-05-04 | 0 | 0 | 0 | 15 | 0 | 0 | 15 | 10 | 0.32018
| Delahaye 135 | 2020-05-08 | 2020-05-29 | D | Doors | 30% |  |  | 0 | 0 | 2020-05-08 | 4 | 0 | 0 | 16 | 0 | 4.8 | 11.2 | 10 | 0.71657
| 1st Visit |  | 2020-05-15 | B | Overview | 100% |  |  | 1 | 1 | 2020-05-15 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1.3571
| 2nd Visit |  | 2020-05-29 | B | Delivery | 0% |  |  | 1 | 0 | 2020-05-29 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 3.2462
| Talbot-Lago T23 | 2020-05-07 | 2020-05-29 | C | Clutch | 100% |  |  | 0 | 1 | 2020-05-07 | 3 | 0 | 0 | 17 | 17 | 0 | 0 | 10 | 3.17
PostWar | [18 empty] | 10 | 2.5815
| Giulietta SS 1300 | 2020-06-01 | 2020-06-19 | A | Chromes | 0% |  |  | 0 | 0 | 2020-06-01 | 20 | 0 | 0 | 15 | 0 | 0 | 15 | 10 | 4.7503
| Delahaye 135MS | 2020-06-08 | 2020-06-30 | C | Paint | 55% |  |  | 0 | 0 | 2020-06-08 | 25 | 0 | 0 | 17 | 0 | 9.35 | 7.65 | 10 | 3.5666
| 1st Visit |  | 2020-06-15 | B | Overview | 100% |  |  | 1 | 1 | 2020-06-15 | 30 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0.85308
| 2nd Visit |  | 2020-06-22 | B | Delivery | 0% |  |  | 1 | 0 | 2020-06-22 | 35 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 2.2255
| Corvette | 2020-06-15 | 2020-06-26 | D | Assembly | 30% |  |  | 0 | 0 | 2020-06-15 | 30 | 0 | 0 | 10 | 0 | 3 | 7 | 10 | 2.3195
Week Labels
| Week | Week | Time | Dummy | Start | End
| 4/5-8/5 | Week 1 | 0 | 0 | 2020-05-04 | 2020-05-08
| 11/5-15/5 | Week 2 | 5 | 0 | 2020-05-11 | 2020-05-15
| 18/5-22/5 | Week 3 | 10 | 0 | 2020-05-18 | 2020-05-22
| 25/5-29/5 | Week 4 | 15 | 0 | 2020-05-25 | 2020-05-29
| 1/6-5/6 | Week 5 | 20 | 0 | 2020-06-01 | 2020-06-05
| 8/6-12/6 | Week 6 | 25 | 0 | 2020-06-08 | 2020-06-12
| 15/6-19/6 | Week 7 | 30 | 0 | 2020-06-15 | 2020-06-19
| 22/6-26/6 | Week 8 | 35 | 0 | 2020-06-22 | 2020-06-26
| 29/6-3/7 | Week 9 | 40 | 0 | 2020-06-29 | 2020-07-03
Formulas:
Ref. Date = IF([Is Event]=1,[End],[Project Details])
Chart Values = NETWORKDAYS(D1,[Ref. Date])-1
Task Length = NETWORKDAYS([Project Details],[End])*(1-[Is Event])
Deliverable = [Deliverable, row above]+7
Completion = [Deliverable]+4
Completion = [Completion, row above]+7